## Phase-1
SHOMA RM Open Items Task List | Time Estimate | Status | Priority | Start Date | End Date | Dependency | Comments | Comments | Teams | Comments from Tania | Pending from Shoma
TENANT Registration / Resident Portal:
Amenities Reservation |  | Completed |  |  | 2020-07-02 |  |  |  | Nirvitech
Community/club joining or creation -Tenant |  | In-Progress |  |  | 2020-07-02 | Shoma Team |  | 1) where should we place the link for community clubs, inside "My Community" page or we need to add new menu for Community club like my community and have links there for create/ join community club. 2) who will approve the club? and after creating club , we will show that club in the join club list or it will be added to the list after its approved. | Thinkersteps | 1. Design made by Joey is Approved 2. THE CLUB WILL AUTOMATICALLY BE APPROVED, BUT ADMIN RESERVES THE RIGHT TO “REMOVE” CLUB INFORMATION IF FOUND INAPPROPRIATE OR NO LONGER RELEVANT. ADD “Disclaimer/Agree to Terms
Recurring Payment Creation and Schedule |  | In-Progress |  |  |  | Shoma Team | Entire work flow on how the payments will funtion. ( Change the look of the payment page?) , Have simple 3 options, and select dates from 1,2,3, dates of the month - Tania has explained this. - DONE |  | Nirvitech | When a tenant makes an online payment, the system should automatically ask, “Would you like to set up recurring payments?”. If so, the program should automatically link them to the “Recurring Payments setup”. Once in SET UP RECURRING PAYMENTS- Fields needed are: 1) Pay From; 2) Payment Amount, 3) Payment Date should be automatically the 1st. However allow a drop box with the 2nd, and 3rd. Add terms and conditions.
Joining of Events – Tenant |  | Completed |  |  | 2020-07-02 |  | Question: Paid or Free Events, how will the payments happen? Type of events? no Approval - Just for information, can only see and only admin |  | Nirvitech | Website will only announce Events and provide information. Admin will include in the information if it is free or if there is a cost. Nothing related to the events will be handled by the website. Any fees will be collected at the time of the event. This section is only for information purposes.
Notification About Event, Rent, Notice, Service Approved etc. |  | NYS |  |  | 2020-07-02 | Shoma Team | Check if need a application for handheld device? (eg: Ipad for uploading pics of maintenance service completed ?) - For now we dont need to upload it | Where all notifications will be required ( Admin+ Tenant portal) What all items require Notifications? | Thinkersteps
Docusign / Leasing workflow (Bluemoon) |  | In-Progress |  |  | 2020-07-02 |  |  |  | Nirvitech / Thinkersteps
Correct the sitewide validations |  | In-Progress |  |  | 2020-07-02 |  |  |  | Nirvitech
Service Requests - In-Progress |  | In-Progress |  |  | 2020-07-02 |  |  |  | Nirvitech
Overall Design (UX/UI) changes / improvements |  | In-Progress |  |  | 2020-07-02 |  |  | Joey is goint to give all UI designed files and we need to convert to html or we will create some designs ourself? | Thinkersteps
Establish complete end-end workflow for a prospect from registration to resident |  | In-Progress |  |  | 02-15-2020 |  |  |  | Nirvitech
Bug Fixes |  | In-Progress |  |  | 02-15-2020 |  | High priority and critical Bugs to be resolved |  | Nirvitech / Thinkersteps
API Integration
Blue Moon API integration |  | NYS |  |  |  | Shoma Team | Check if Kathy has customized the documents. | login worked with the credeintials given by bluemoon customer support using there swagger tool provided to test the api. but not with Rest client like ARC/ Web service. so we need credentials which will give us positive responce. may be swagger tool has some default parameters. which we are not sending | Thinkersteps
Implementation of SMS and email services (Twilio API integration) |  | NYS |  |  | 02-15-2020 |  | Credentials provided. |  | Thinkersteps
ACUTRAQ API integration |  | NYS |  |  |  | Shoma Team |  | The credentials provided gives Invalid request to login with api | Thinkersteps
ADMIN:
Admin Level access to the Resident Portal |  | NYS |  |  | 2020-07-02 |  | What funtion admin can perform in Resident portal | Are there any level's of acess in Admin? | Nirvitech | Admin should not have access to “Resident portal” or tenants accounts other than to The Community section. Only Admin functions related to Resident portal’s activities, such as reservation of amenities, etc.
Approval of Community/club joining or creation -admin |  | NYS |  |  | 2020-07-02 |  | Check with Tania if the workflow is same for the Tenant and Admin, she has sent this to us already. - DONE |  | Thinkersteps
Approval of Reservations |  | NYS |  |  | 2020-07-02 |  | What type of reservations/ paid or free? Cancellation of a reservation Deposit? |  | Nirvitech | As mentioned on the call, the tenant requests the reservation, Admin must confirm “Approve” that the date is available. When tenant receives the approval notice, they are directed to make the reservation payment and advised that the “Security Deposit” is due 3 days (72 hours) prior to the event. If the Security Deposit is not received 3 days before the event, the event will be cancelled. The Reservation payment is refundable if the event is cancelled at least three days prior to the event. Once the reservation payment is made, Admin confirms “Reserved” to the tenant. Three days before the scheduled event, an automatic reminder with payment link is sent to the resident for the Security deposit amount. Once the security deposit is received, Admin changes status to “Completed” and an automatic email/text is sent to the tenant, letting them know that the Security Deposit has been received and that the reservation payment made is no longer refundable. If tenant cancels the event within the approved time, Admin gets notification “Status=Cancelled” and processes a refund which generates a credit memo to the tenant’s account.
Approval of Lease |  | NYS |  |  | 2020-07-02 |  |  |  | Nirvitech |  | Lease renewals/ expirations
Event Management -admin |  | NYS |  |  | 2020-07-02 |  | Paid events, non- paid events |  | Nirvitech
Notifications to property manager, Tenant, etc. |  | NYS |  |  | 2020-07-02 |  | notifications will be as web only i.e signal R or if we are going to use mobile/tab? |  | Thinkersteps
Dashboard creation - Admin dashboard |  | NYS |  |  | 2020-07-02 | Shoma Team | Tania has provided us the list of items for dashboard |  | Nirvitech | ADMIN DASHBOARDS- Accounting District Manager Leasing Manager Property Manager Leasing Agents Superintendent Grounds Keeper
Service Request Management -admin |  | In-Progress |  |  | 2020-07-02 |  |  |  | Nirvitech
Amenity Management -admin |  | NYS |  |  | 2020-07-02 |  | Cancellation policy ? Admin side- Approval process, is there a refund provided in case of cancellation? |  | Nirvitech
Lease Management -admin |  | NYS |  |  | 2020-07-02 |  | Ask regarding extension of lease, work-flow, Email- when the lease expires. |  | Nirvitech
Unit Move-In and Move-out management -admin |  | NYS |  |  | 2020-07-02 | Shoma Team | Need more details of the workflow, ( check the requiremnts for check-in and check-out, condition of fans, lights etc, any damaged goods , broken items etc |  | Nirvitech |  | Move-in and Move-out procedures
Late Payment Management -admin |  | NYS |  |  | 2020-07-02 |  | Setup this, how will this work, time of payment, per month/ per week. What are the charges? |  | Nirvitech |  | Utility charges, late payment fees , Misc billing , service invocies
Guest Management -admin |  | NYS |  |  | 2020-07-02 |  | Check for the Approval Flow from Admin automatic approval | When a tenant completes a guest management card, the Leasing Manager and leasing agents receive a notification in their dashboard. The completed guest management card is kept in the document section of the Tenant Portal. Once management approves the guest card, they send an auto message to the tenant with a link to print a parking pass which will have the approved dates written on it. Format to be advised. | Nirvitech
Connect to the Renters Insurance API |  | NYS |  |  | 02-15-2020 | Shoma Team | Clarity regarding renters insurance process |  | Nirvitech
Work Order - Admin |  | NYS
Work order forms |  | NYS | [7 empty] | Tania has provided the workflow and the sample forms.
Bond services |  | NYS
Welcome letter |  | NYS

## Phase-2
SHOMA RM Open Items Task List | Time Estimate | Status | Priority | Start Date | End Date | Dependency | Comments | Teams
API Integration:
Sage Integration |  |  | Phase-2 |  |  | Shoma Team
Report generation |  |  | Phase-2
Feature
Lead Source Attribution |  |  | Phase-3
CRM
Make the application PCI compliant |  | NYS |  |  |  | Shoma Team | Check on what type of compliance they require
Guest Parking pass
Accounting
Advertising/ Marketing