## Phase-1
SHOMA RM Open Items Task List | Time Estimate | Status | Priority | Start Date | End Date | Dependency | Comments | Teams |  | Need from Shoma
TENANT Registration / Resident Portal: | [9 empty] | More information on the Payment workflow as discussed in yesterday's call
Amenities Reservation |  | In-Progress |  |  | 2020-07-02 |  |  | Nirvitech |  | Service Requests Task workflow
Community/club joining or creation -Tenant |  | NYS |  |  | 2020-07-02 | Shoma Team | Need more details of the workflow. | Thinkersteps |  | Acutrack account for Shoma
Recurring Payment Creation and Schedule |  | NYS |  |  |  | Shoma Team | Check with Tania on the workflow for this, she did however explain it on the call. | Nirvitech |  | Sage API integration related details
Joining of Events – Tenant |  | NYS |  |  | 2020-07-02 |  |  | Nirvitech
Notification About Event, Rent, Notice, Service Approved etc. |  | NYS |  |  | 2020-07-02 | Shoma Team | Check if need a application for handheld device? (eg: Ipad for uploading pics of maintenance service completed ?) | Thinkersteps
Docusign / Leasing workflow (Bluemoon) |  | In-Progress |  |  | 2020-07-02 |  | Nirvitech will transfer knowledge to Lalits team for this item | Nirvitech / Thinkersteps
Correct the sitewide validations |  | In-Progress |  |  | 2020-07-02 |  |  | Nirvitech
Service Requests - In-Progress |  | In-Progress |  |  | 2020-07-02 |  |  | Nirvitech
Overall Design (UX/UI) changes / improvements |  | In-Progress |  |  | 2020-07-02 |  | Joey to work along with Lalits team for the design | Thinkersteps
Establish complete end-end workflow for a prospect from registration to resident |  | In-Progress |  |  | 02-15-2020 |  |  | Nirvitech
Bug Fixes |  | In-Progress |  |  | 02-15-2020 |  | High priority and critical Bugs to be resolved | Nirvitech / Thinkersteps
API Integration
Blue Moon API integration |  | NYS |  |  |  | Shoma Team | Check if Kathy has customized the documents. | Thinkersteps
Implementation of SMS and email services (Twilio API integration) |  | NYS |  |  | 02-15-2020 |  |  | Thinkersteps | Ties with - 7
ACUTRAQ API integration |  | NYS |  |  |  | Shoma Team |  | Thinkersteps
ADMIN:
Admin Level access to the Resident Portal |  | NYS |  |  | 2020-07-02 |  |  | Nirvitech
Approval of Community/club joining or creation -admin |  | NYS |  |  | 2020-07-02 |  | Check with Tania if the workflow is same for the Tenant and Admin, she has sent this to us already. | Thinkersteps
Approval of Reservations |  | NYS |  |  | 2020-07-02 |  |  | Nirvitech
Approval of Lease |  | NYS |  |  | 2020-07-02 |  |  | Nirvitech
Event Management -admin |  | NYS |  |  | 2020-07-02 |  |  | Nirvitech
Notifications to property manager, Tenant, etc. |  | NYS |  |  | 2020-07-02 |  |  | Thinkersteps
Dashboard creation |  | NYS |  |  | 2020-07-02 | Shoma Team | Need details from the Shoma team as to how this will look like. What are the items to be mentioned here. | Nirvitech
Service Request Management -admin |  | In-Progress |  |  | 2020-07-02 |  |  | Nirvitech
Amenity Management -admin |  | NYS |  |  | 2020-07-02 |  |  | Nirvitech
Lease Management -admin |  | NYS |  |  | 2020-07-02 |  |  | Nirvitech
Unit Move-In and Move-out management -admin |  | NYS |  |  | 2020-07-02 | Shoma Team | Need more details of the workflow. | Nirvitech
Late Payment Management -admin |  | NYS |  |  | 2020-07-02 |  |  | Nirvitech
Guest Management -admin |  | NYS |  |  | 2020-07-02 | Shoma Team | Check for the Approval Flow from Admin | Nirvitech
Connect to the Renters Insurance API |  | NYS |  |  | 02-15-2020 | Shoma Team |  | Nirvitech

## Phase-2
SHOMA RM Open Items Task List | Time Estimate | Status | Priority | Start Date | End Date | Dependency | Comments | Teams
API Integration:
Sage Integration |  |  | Phase-2 |  |  | Shoma Team
Report generation |  |  | Phase-2
Feature
Lead Source Attribution |  |  | Phase-3
CRM
Make the application PCI compliant |  | NYS |  |  |  | Shoma Team | Check on what type of compliance they require